Scale-SETI Project Roadmap and Scope Control

Publication, Engineering, Review, and Experimental Plan

Version 1.1
Tim Boccaleri
September 2026

If a new item does not close a defined publication, reproducibility, review, or experimental gap, it does not belong in the current artifact.

# 1. Purpose

This roadmap prevents scope drift and defines what each Scale-SETI artifact is supposed to accomplish. The project will no longer add material simply because additional detail is possible. Each document has a defined audience, stopping condition, and next action.

# 2. Project Architecture

## Product A - Core Concept Paper

Purpose: Present the intellectual contribution, scientific motivation, falsifiable research question, evidence standards, relationship to prior work, and high-level experimental roadmap.

Primary audience: Physicists, SETI/technosignature researchers, information theorists, experimentalists, reviewers, and potential collaborators.

Baseline: Revision 5 technical-review edition.

What belongs here:

central Scale-SETI hypothesis and search-space framing

established science versus speculative extensions

minimal scale-coordinate framework

relationship to prior work

falsifiability and evidence ladder

high-level Phase-1 experimental design

major objections and limitations

publication-quality references

up-scale SETI as a conceptual/distributed-analysis branch distinct from the Phase-1 microscopic bench

bidirectional macro/micro model showing that our regime may be intermediate rather than privileged

wall analogy as the accessible conceptual explanation of a shared boundary interface

expanded SETI search-space framework: same-scale, down-scale, and up-scale search

What does not belong here:

connector pinouts

full wiring schedules

detailed procurement BOMs

calibration worksheets

software repository internals

fabrication drawings

step-by-step bench assembly

Target size/scope: 25-35 pages including references and essential figures.

Definition of done:

1. hypothesis clear and internally consistent

2. established science separated from speculation

3. novelty and prior work accurately represented

4. falsifiable proposition explicit

5. evidence and failure criteria defined

6. major objections addressed

7. external reviewers given opportunity to critique

8. remaining changes limited to scientific accuracy, clarity, or reviewer response

## Product B - Phase-1 Technical Design Package

Purpose: Allow an independent instrumentation/microfluidics laboratory to reproduce the first controlled experiment without guessing important design decisions.

Primary audience: Instrumentation engineers, microfluidics researchers, electronics engineers, experimental physicists, software/data engineers, and replication labs.

Baseline: Phase-1 Design Package v0.3.

What belongs here:

complete architecture

electrical and fluidic schematics

wiring and I/O maps

mechanical/fabrication drawings

BOM and alternates

host/network isolation design

software interfaces and schemas

calibration procedures

control matrix

acceptance criteria

bring-up procedure

troubleshooting and replication instructions

release manifests and hashes

Target size/scope: As long as needed for complete reproducibility.

Definition of done:

1. critical components identified by part number or performance specification

2. every intentional signal path documented

3. relevant leakage paths mitigated or measured

4. all electrical/fluidic interfaces documented

5. calibration and acceptance procedures executable

6. data schemas and interfaces validated

7. another qualified lab can build from the package

8. unresolved decisions non-critical or explicitly documented

## Product C - Experimental Results Paper

Purpose: Report actual experimental results, including null results, after commissioning and preregistration.

Primary audience: Scientific reviewers and the broader research community.

Baseline: Created only after real data exist.

What belongs here:

final apparatus used

deviations from Design Package 1.0

preregistered hypotheses and analysis

calibration and acceptance results

control results

blinded trial results

statistics and uncertainty

anomaly investigation

raw-data availability

independent replication status

Target size/scope: Determined by results and target venue.

Definition of done:

1. real experimental data exist

2. analysis follows preregistration

3. results and controls are complete

4. data and code are archived

# 3. Current Project Status

| Milestone | Status | Notes |
| --- | --- | --- |
| Original idea | Complete | Search for intelligence across physical scale |
| Conceptual hypothesis | Complete | Hierarchical / nonlinear scale framing |
| Scientific framing | Complete | Established science separated from speculation |
| Falsifiability framework | Complete | Challenge-response and control hierarchy defined |
| Formal technical review | Complete | Revision 5 |
| Phase-1 reference architecture | Complete | Known-physics validation bench |
| Engineering control documents | Complete | Through v0.3 |
| Stage-1 implementation choice | Complete | Ion concentration / microfluidic reference channel |
| Dry-run software/data pipeline | Complete | Synthetic campaign demonstrated |
| Fabrication/build release | NEXT | Close remaining reproducibility gaps |
| External expert review | Pending | NEXT publication gate |
| Concept Paper Candidate 1.0 | Complete | Expanded same-scale/down-scale/up-scale framework; ready for external review |
| Public preprint / DOI | Pending | Zenodo / OSF first |
| Physical prototype | Pending | After design review |
| Commissioning | Pending | Acceptance gates before search experiment |
| Search experiment | Pending | Only after validated baseline |
| Results paper | Pending | Based on real data |

Scope boundary added in v1.1: the up-scale SETI concept belongs to Product A. It does not reopen the Phase-1 microscopic engineering scope. Any future distributed up-scale sensor/probe architecture is deferred until after Concept Paper 1.0 review and publication planning.

# 4. Remaining Work Before External Review

Complete only the engineering items necessary for a competent external reviewer to evaluate reproducibility and failure modes.

dimensioned receiver-cell / flow-cell drawing

complete electrical schematic with component values

grounding, shielding, and isolation schematic

fluidic assembly drawing

connector and pin schedule

final procurement BOM with quantities, alternates, and performance requirements

physical cable-routing and zone-boundary drawing

bench assembly procedure

bench bring-up sequence

troubleshooting matrix

acceptance-test procedure and forms

list of unresolved engineering assumptions

# 5. External Technical Review Plan

The goal of external review is criticism, not endorsement. Seek 5-10 contacts across molecular communication, microfluidics, nanosensors, experimental physics, instrumentation, statistics/information theory, quantum measurement, and SETI/technosignatures.

Core reviewer questions:

1. Is there a known conventional physical pathway that invalidates the isolation logic?

2. Are the positive, negative, sham, delayed, replay, clock, and network controls sufficient?

3. Are the statistical thresholds and multiple-testing controls defensible?

4. Is important prior work missing?

5. Does existing literature make the proposal non-novel?

6. Could another lab reproduce Phase 1 from the package?

7. Which assumptions require direct measurement before confirmatory work?

8. What result would justify escalation?

Review disposition categories:

Critical - must be resolved before release

Major - normally resolved before release

Minor - clarity or non-critical implementation improvement

Deferred - valid but outside current scope

Rejected with rationale - reviewed but not adopted

# 6. Publication Plan

## Stage 1 - Candidate Release

Use the completed Concept Paper Candidate 1.0 as the publication-review baseline; do not expand it except to answer scientific/reviewer gaps.

## Stage 2 - Public Preprint and Research Record

After feedback, publish Concept Paper 1.0 on a DOI-bearing repository such as Zenodo; create an OSF project for protocols, preregistration, data, code, and updates; archive the design package and release hashes.

## Stage 3 - arXiv / scholarly distribution

Attempt an appropriate arXiv submission once mature and category/endorsement requirements are addressed.

## Stage 4 - Journal or conference submission

Choose the venue after review; the concept paper and later experimental-results paper may require different venues.

# 7. Build and Experiment Plan

## Phase 1A - Known-Physics Commissioning

Prove the challenge generation, microscopic communication, isolation, blinded analysis, telemetry, controls, scoring, and 100-trial commissioning pipeline. No claim about another scale is tested.

## Phase 1B - Stronger Isolation / Alternative Microscopic Interface

Only after Phase 1A passes. Change one physical layer at a time while keeping the protocol fixed.

## Phase 2 - Search Experiment

Only after commissioning and external review. Remove or block the known information path while retaining blinded challenge/receiver infrastructure. Reproducible challenge-linked information dependence is the target.

## Phase 3 - Independent Replication

Any serious candidate must be reproduced by independent laboratories with fresh challenges and independent implementations.

# 8. Scope-Control Rules

1. Which product does the item belong to?

2. Which defined gap does it close?

3. Is it required before the next project gate?

4. Could it be deferred without weakening the deliverable?

5. Does it introduce a new unvalidated assumption or testing burden?

No feature is added to Phase-1 Design Package 1.0 unless it is necessary to reproduce, validate, isolate, analyze, or safely operate the defined Phase-1 experiment.

# 9. Change-Control Process

After Candidate 1.0, substantive changes receive an identifier in the form SETI-CR-YYYY-NNN. Each request records the requested change, reason, artifact affected, risk if omitted, new assumptions, verification required, disposition, approver, and date.

# 10. Immediate Next Actions

1. Complete remaining fabrication/build closure items.

2. Produce Phase-1 Technical Design Package Candidate 1.0.

3. Use the completed Concept Paper Candidate 1.0 as the publication-review baseline; do not expand it except to answer scientific/reviewer gaps.

4. Build an external-review packet with both candidate documents and a one-page reviewer guide.

5. Send to targeted reviewers and log feedback.

6. Resolve Critical and Major findings.

7. Freeze Concept Paper 1.0 and Design Package 1.0.

8. Publish the concept/preprint and repository record.

9. Only then authorize significant Phase-1 hardware procurement and physical build.

# 11. Definition of Project Success

a clearly defined and falsifiable search concept

a reproducible experimental methodology

a high-quality null result or reproducible anomaly

public data, protocols, and code sufficient for independent scrutiny

a clear scientific record separating observation from interpretation

The project should never define success as obtaining a preferred outcome.

# 12. Final Stop Rule

At that point, we stop expanding documents and start testing the experiment.